## Sheet1
Date | Discussed | Achievement since last meeting | Action points for next meeting | Comments
2022-03-16 | Discussed ideas for the project | NA | Start thinking about design. Read Constructivist learning theory information sent by email
2022-03-24 | Discussed initial design and project proposal | Read Constructivist learning theory material and started thinking about desing | Start application for ethics approval
2022-03-31 | Discussed the project proposal and ethics approval | Started ethics approval process | Complete and submit ethics approval
2022-04-07 | Ethics proposal and some game ideas | Did more of ethics application, but didn't complete | Complete and submit ethics approval | Didn't submit ethics application, because I had more questions
2022-04-14 | Discussed research | Submitted ethics approval | Do research and put notes into table
2022-04-28 | Discussed changes to be made to ethics application | Did some reading and put notes into a table | Make changes to ethics application and resubmit
2022-05-05 | Discussed ideas for challenges and technologies | Re-submitted ethics application, which has now been sent to the board | Continue research and start implementation
2022-05-12 | Discussed progress | Research mostly complete. Set up Unity project and purchased sprites | Work on implementation and preliminary report
2022-05-19 | Preliminary report | Started preliminary report. Coninued implementation | Work on report and implementation
2022-05-26 | Feedback on part of preliminary report | Continued implementation and report | Complete more of preliminary report
2022-06-02 | Feedback on preliminary report draft. Ethics board changes | Worked more on report and implentation | Make changes to ethics application and submit report
2022-06-09 |  |  |  | Didn't meet because Karsten had Covid
2022-06-16 |  |  |  | Didn't meet because Bryony had Covid
2022-06-23 | Discussed the plan for while Karsten is on leave | Got ethics approval. Submitted report | Lots of implementation
29/06 - 28/07 |  |  |  | Didn't meet because Karsten on leave
2022-08-11 | Feedback from markers on preliminary report | Created character module. Did user testing. Started city sceen, animations, movement, collisions, depth sorting etc | Make changes based on user testing feedback
2022-08-18 | Looked at game so far | Made changes to character module | Lots of good pointers for character module
2022-08-25 | Ideas for challenges in the city | Made changes to character module. Started first challenge for city | Make more challenges for the city
2022-09-01 | Draft report. Implementation | Worked on list challenge. Completed sprites and animations for character | Work on draft report
2022-09-08 | Draft report. List challenge | Worked on draft report | Improve list challenge, submit draft report, add more challenges, testing
2022-09-15 | Report. Challenges. Testing | Improved list challenge. Submitted report | Add more challenges. Do more testing. Refactor code
2022-09-22 | The draft report and what is missing | Added a challenge on conditionals, started to refactor code, tests for list challenge | Add at least one more challenge
2022-09-29 | The snap shot and the final report | Added three more challenges and concluded the game. Did more unit testing | Do last round of user testing and work on the report
2022-10-06 | User testing and the report | Completed first two user tests, made some improvements and did more work on the report | Finish user testing and get draft of report to Karsten by Tuesday | Didn't finish user testing as participants weren't available until later in the week
2022-10-13 | Feedback from report and demoed the game | Finish the report by due time | Start work on presentation